## Instructions
Case Study Project Tracker
Java Full Stack Training — Capstone Case Study
How to use this workbook
1. Go to the 'Task Tracker' sheet. Each trainee/team lists the tasks (modules, features, sub-tasks) for their case study there — similar to a sprint backlog in a real software team.
2. Update your task's Status, % Complete, and Hours Spent regularly (daily/every alternate day) — do not wait until the deadline.
3. Use the 'Daily Work Log' sheet every working day to record what you did, like a standup update: Yesterday's work, Today's plan, and any blockers.
4. The 'Dashboard' sheet updates automatically from the Task Tracker sheet — do not edit it directly.
5. Cells shaded light yellow are example rows — replace them with your own data. Do not delete the header rows.
Column & Status Legend (Task Tracker sheet)
Status values: Not Started, In Progress, Blocked, In Review, Completed
Priority values: High, Medium, Low
% Complete: enter a whole number between 0 and 100 (e.g., 50 for 50%).
Hours Estimated / Hours Spent: enter numeric hours (e.g., 4, 6.5).
Remarks / Blockers: mention any dependency, doubt, or issue blocking progress — leave blank if none.
Column Legend (Daily Work Log sheet)
Fill one row per person per working day. Task ID should match the Task Tracker sheet where applicable.
Conventions used in this workbook
Yellow fill = example row / cells you should edit or replace with your own data.
White/grey rows = your data entry rows (add as many as needed).
Dashboard values and charts = auto-calculated, formula-driven — do not overwrite.
Team: Sriram, Akash, Nitish, Harsha — tasks are split equally (15 estimated hours each). See "Team Workload Split" on the Dashboard.

## Task Tracker
Case Study Task Tracker
Update Status, % Complete and Hours Spent regularly. See 'Instructions' sheet for the legend.
Task ID | Module / Feature | Task Description | Assigned To | Priority | Status | Start Date | Due Date | Est. Hours | Hours Spent | % Complete | Remarks / Blockers | Last Updated
T-001 | Database / Entities | Create entity classes and relationships for all tables (UserLogin, Patient, Doctor) | Sriram | High | Completed | 2026-09-30 | 2026-09-30 | 1 | 1.5 | 100 | None
T-002 | Database / Entities | Create entity classes and relationships for tables ( Appointment, Address) | Harsha | High | Completed | 2026-09-30 | 2026-09-30 | 1 | 1 | 100 | None
T-003 | Database / Entities | Create entity classes and relationships for tables ( Bill, Medicine) | Nitish | High | Completed | 2026-09-30 | 2026-09-30 | 1 | 1 | 100 | None
T-004 | Database / Entities | Create entity classes and relationships for tables ( Prescription, Prescription Items) | Akash | High | Completed | 2026-09-30 | 2026-09-30 | 1 | 1 | 100 | None
T-005 | Database / Repositories | Create Spring Data JPA repository interfaces for all entities | Nitish | High | Completed | 2026-10-01 | 2026-10-01 | 1 | 1 | 100 | None
T-006 | DTO Layer | Create request and response DTOs (Java records) with validation annotations | Harsha | High | Completed | 2026-10-01 | 2026-10-01 | 2 | 1 | 100 | None
T-007 | Patient & Doctor Management | Patient and Doctor services: register, get by id / user id, get all, doctors by department, update, delete | Sriram | High | Completed | 2026-10-02 | 2026-10-02 | 5 | 6 | 100 | Written, waiting for testing
T-008 | Appointment Booking | Appointment service: book with doctor slot-overlap check, cancel, reschedule, get by patient / doctor / date, update status | Nitish | High | Completed | 2026-10-02 | 2026-10-02 | 3 | 4 | 100 | Fixed 30-minute slot length to be confirmed with sir
T-009 | Prescription & Address | Prescription service (create / update with items) and Address service (save or update, get) | Akash | Medium | Completed | 2026-10-02 | 2026-10-02 | 5 | 5 | 100 | Waiting for testing
T-010 | Billing & Medicine | Bill service (consultation and medicine bills, update status) and Medicine service (add, search, update, delete) | Nitish | Medium | Completed | 2026-10-02 | 2026-10-02 | 4 | 3 | 100 | Waiting for testing
T-011 | Exception Handling | Global exception handler with custom exceptions mapped to proper HTTP status codes | Sriram | Medium | Completed | 2026-10-02 | 2026-10-02 | 3 | 1 | 100 | Handlers for newer exceptions to be added and tested
T-012 | REST Controllers | REST controllers for all 8 modules with validation and consistent URL style | Sriram | High | Completed | 2026-10-03 | 2026-10-03 | 8 | 12 | 100 | Fixed path variable bug in AppointmentController
T-013 | Frontend - Setup & Login | React setup, auth context, protected routes by role, login page, API service | Sriram | High | Completed | 2026-10-04 | 2026-10-04 | 4 | 4 | 100 | Role names in roles.js must match the backend Role enum
T-014 | Frontend - Layout | Login layout and main layout with Navbar and Sidebar (menu per role) using MUI | Nitish | Medium | Completed | 2026-10-04 | 2026-10-04 | 6 | 6 | 100 | None
T-015 | Frontend - Appointment Booking | Book appointment page: choose department, doctor, date and time (sir's main requirement) | Akash | High | Completed | 2026-10-04 | 2026-10-04 | 2 | 3 | 100 | Needs login and layout done first
T-016 | Frontend - Management Pages | Patients, Doctors and Appointments list pages with add / edit / cancel | Harsha | Medium | Completed | 2026-10-04 | 2026-10-04 | 2 | 3 | 100 | None
T-017 | Frontend - Clinical Pages | Medicines, Prescriptions and Bills pages | Harsha | Medium | Completed | 2026-10-05 | 2026-10-05 | 4 | 5 | 100 | None
T-018 | Testing | Test all APIs in Postman: add doctor, register patient, login, book appointment, prescription, bill | Akash | High | Completed | 2026-10-05 | 2026-10-05 | 7 | 3 | 100 | None

## Daily Work Log
Daily Work Log
Fill one row per person per working day — like a daily standup update.
Date | Participant Name | Task ID | Work Done Today | Hours Spent | Status | Blockers / Issues | Plan for Tomorrow
2026-09-30 | Sriram | T-001 | Create entity classes and relationships for all tables (UserLogin, Patient, Doctor) | 1.5 | Completed | None | Repository and Service layers
2026-09-30 | Harsha | T-002 | Created entity classes and relationships for tables ( Appointment, Address) | 1 | Completed | None | Service layers for the created Entities
2026-09-30 | Nitish | T-003 | Create entity classes and relationships for tables ( Bill, Medicine) | 1 | Completed | None | Service layers for the created Entities
2026-09-30 | Akash | T-004 | Create entity classes and relationships for tables ( Prescription, Prescription Items) | 1 | Completed | None | Service layers for the created Entities
2026-10-01 | Nitish | T-005 | Created Spring Data JPA repository interfaces for all entities | 1 | Completed | None | Implementation Of Service layers
2026-10-01 | Harsha | T-006 | Created request and response DTOs (Java records) for all modules | 2.5 | In Progress | None | Add validation annotations to the DTOs
2026-10-02 | Harsha | T-006 | Added validation annotations (@NotNull, @Size, @Email) to all DTOs | 2.5 | Completed | None | Start REST controllers for all modules
2026-10-02 | Sriram | T-007 | Patient and Doctor services: register, get by id / user id, get all | 3 | In Progress | None | Doctors by department, update and delete
2026-10-02 | Nitish | T-008 | Appointment service: book with doctor slot-overlap check and cancel | 2 | In Progress | None | Reschedule, get by patient / doctor / date, update status
2026-10-02 | Nitish | T-010 | Bill service: consultation and medicine bills | 1.5 | In Progress | None | Update bill status and start Medicine service
2026-10-02 | Akash | T-009 | Prescription service: create and update with items | 2 | In Progress | None | Address service (save or update, get)
2026-10-05 | Harsha | T-012 | REST controllers for the modules with validation and consistent URL style | 5 | In Progress | None | Finish remaining controllers and start frontend setup
2026-10-05 | Sriram | T-007 | Patient and Doctor services: doctors by department, update, delete | 3 | In Review | Written, waiting for testing | Global exception handler
2026-10-05 | Nitish | T-008 | Appointment service: reschedule, get by patient / doctor / date, update status | 2 | In Review | Fixed 30-minute slot length to be confirmed with sir | Support API testing of appointment module
2026-10-05 | Nitish | T-010 | Medicine service (add, search, update, delete) and bill status update | 1.5 | In Progress | None | Final checks on billing and medicine
2026-10-05 | Akash | T-009 | Address service: save or update, get | 2 | In Progress | None | Review prescription and address services
2026-10-06 | Sriram | T-012 / T-013 | Finished REST controllers; React setup, auth context and protected routes | 7 | In Progress | Role names in roles.js must match the backend Role enum | Login page and API service
2026-10-06 | Sriram | T-011 | Global exception handler with custom exceptions mapped to HTTP status codes | 3 | In Review | Handlers for newer exceptions to be added and tested | Start Patients and Doctors pages
2026-10-06 | Nitish | T-010 | Reviewed Bill and Medicine services | 1 | In Review | Waiting for testing | Start Medicines, Prescriptions and Bills pages
2026-10-06 | Akash | T-009 | Reviewed Prescription and Address services | 1 | In Review | Waiting for testing | Start Postman API testing

## Dashboard
Project Tracker Dashboard
Auto-calculated from the 'Task Tracker' sheet — do not edit these cells.
Task Status Summary
Total Tasks | 18
Not Started | 0
In Progress | 0
Blocked | 0
In Review | 0
Completed | 18
Effort Summary
Total Est. Hours | 60
Total Hours Spent | 61.5
Avg. % Complete | 100
Status | Count |  | Metric | Hours
Not Started | 0 |  | Est. Hours | 60
In Progress | 0 |  | Spent Hours | 61.5
Blocked | 0
In Review | 0
Completed | 18
Team Workload Split
Member | Tasks | Est. Hours | Hours Spent | Share of Est. Hours | Avg. % Complete
Sriram | 5 | 21 | 24.5 | 35% | 100%
Akash | 4 | 15 | 12 | 25% | 100%
Nitish | 5 | 15 | 15 | 25% | 100%
Harsha | 4 | 9 | 10 | 15% | 100%
Total | 18 | 60 | 61.5 | 100% | 100%